## Submission Draft
IncuBrix Engineering Assessment 4 — Submission Form Draft
NOT THE OFFICIAL FORM. The Excel form referenced in the brief was not present. These conservative statuses are evidence-based; replace this draft with IncuBrix’s supplied template before submitting.
Readiness: NOT READY. Native certifications, live demo URL, private GitHub remote/reviewer access, and demo video are missing. Git directory has no commits. Do not present this draft as completed.
Category | Requirement / metric / hard case | Status | Evidence in project | Gap, result or qualification
Must-have | 1. Exact connector contract | Partial | app/; manifests/; openapi.yaml; tests/test_service.py | Implemented locally; reviewer contract suite not run.
Must-have | 2. Six Core connectors certified | No | manifests/; tests/test_service.py | Native certifications absent; certification workflow is simulation only.
Must-have | 3. Add destinations by configuration row | Partial | config/destinations.yaml; app/; tests/test_service.py | Catalogue supports instances; reviewer clean-machine test not run.
Must-have | 4. Frequency, promo, links, disclosure rules | Partial | app/core.py; tests/test_core.py; tests/test_service.py | Individual assertions exist; full assessment rule set not evidenced.
Must-have | 5. Cleanup and 429 handling | Partial | tests/test_service.py; README.md; REPORT.md | Simulation cleanup test source exists; no native instance evidence; timed 429 backoff incomplete.
Must-have | 6. Retry after timeout, same idempotency key | Partial | tests/test_service.py; app/ | Same-key repeat test source exists; timeout injection not tested.
Must-have | 7. Secrets protected and simulation mode | Yes (local code) | .env.example; .gitignore; README.md; app/ | Local code supports simulation/env secret refs; re-scan repo/logs before submission.
Must-have | 8. Compose includes Lemmy and Ghost | No | docker-compose.yml; PROJECT_STATUS.md | Compose starts service/SQLite only.
Must-have | 9. Live demo available through review | No | README.md; PROJECT_STATUS.md | No URL/token or hosting target supplied.
Level | Core level | No | Must-haves above | Must-haves fail/partial; no six native certifications.
Level | Advanced level | No | No importer/reports/capture evidence | CSV import, human-confirmed rules, relevance/tailoring, 3 extra connectors absent or unmeasured.
Level | Outstanding level | No | No recommender/metrics/recertification/catalogue evidence | Outstanding features absent or unmeasured.
Integration | 1. One-command startup + tests | Partial | docker-compose.yml; pyproject.toml; artifacts/test-results.md | Compose config validates; Docker E2E unavailable; Lemmy/Ghost absent.
Integration | 2. OpenAPI 3.1 matches service | Partial | openapi.yaml; app/main.py | Spec exists; exact running-service match not verified.
Integration | 3. Background jobs | Yes (local) | app/main.py; tests/test_service.py | Jobs/status/progress implemented in local code.
Integration | 4. Safe retries on every POST | Partial | tests/test_service.py; app/ | Idempotency/payload conflict source test; timeout retry/all POSTs unverified.
Integration | 5. Shared JSON errors | Partial | README.md; app/ | Error format documented; all provider mappings unverified.
Integration | 6. Environment/configuration | Partial | config/; .env.example; app/ | Config exists; full clean-environment audit incomplete.
Integration | 7. Upload/URL + S3-compatible storage | No | README.md; REPORT.md | Artifact ingest and MinIO/S3 storage not implemented.
Integration | 8. Structured logs + health/readiness | Yes (local) | app/; tests/test_service.py | Routes/logging implemented; live log evidence absent.
Integration | 9. Output manifest complete | Partial | app/core.py; tests/test_core.py | Manifest exists; timings/seed/rights completeness not proven.
Integration | 10. Batch runner | Yes (local) | tools/batch_runner.py; README.md | Runner exists; complete run outputs still needed.
Metric | Native destinations certified per connector | 0 | PROJECT_STATUS.md; REPORT.md | No native certification claimed.
Metric | Core unit tests passed | 7 (recorded) | artifacts/test-results.md | Recorded tests/test_core.py result; dated run log absent.
Metric | HTTP/API suite | Not completed / unknown | artifacts/test-results.md | Result says not completed; rerun in supported environment.
Metric | Publish reliability / retry duplicates | Not measured | No captured retry run | Do not claim zero duplicates on timeout without evidence.
Metric | Rule violations caught/missed | Not measured aggregate | tests/test_core.py; tests/test_service.py | Assertions exist; no labeled set totals.
Metric | Catalogue import performance | Not implemented / measured | No importer/report | Advanced gap.
Metric | Cost per 1,000 publications | Simulation estimate $0 | tests/test_core.py; README.md | Excludes hosting/hardware; no paid provider used in default path.
Hard case | Timeout then retry same key | Partial | tests/test_service.py | Same-key repeat source test; no timeout injection.
Hard case | 429 reset time | Partial | tests/test_core.py; README.md | Retry metadata tested; timed backoff incomplete.
Hard case | Revoked token / rejected content | Partial | app/; README.md | Shared codes documented; captured run absent.
Hard case | Overlong content / unsupported media | Partial | tests/test_core.py; tests/test_service.py | Text limits/content types in sources; media matrix not tested.
Hard case | Weekly cap / prohibited promotion | Partial | tests/test_core.py; tests/test_service.py | Frequency/rule assertions; combined run report absent.
Hard case | Provider field rename and demotion | No | No evidence present | Schema drift recertification/demotion absent.
Hard case | CSV errors/languages/revoked permission | No | No evidence present | Importer and partner permission workflow absent.
Hard case | Non-English community / disclosure | Partial | tests/test_core.py; tests/test_service.py | Disclosure assertion source; language handling/run absent.
External | Private GitHub + admin@incubrix.com access | No | Git has no commits or remote | Create private repo, push real history, invite reviewer.
External | Demo URL / token | No | PROJECT_STATUS.md | Requires hosting target and credentials.
External | Unedited video, <=8 minutes | No | No video in workspace | Show clean run, failure, tests, design decision.
Test pack | Inputs/outputs/failures/logs/evidence index | Partial | examples/requests/; tests/; artifacts/test-results.md; artifacts/test-run-logs/ | Captured logs include default pytest failure, core 7-test pass, and Docker daemon check. Complete outputs and application logs remain missing.
Certification pack | Run/live response/screenshot/deletion proof | No native pack | tests/test_service.py (test source only) | Simulation is not native certification; collect artifacts per destination.
Key rule | Individual work / candidate authorship | Partial | AI_USE.md; project history | Candidate must personally review and attest; independent authorship cannot be verified from this workspace.
Key rule | AI and service disclosure | Yes (documented) | AI_USE.md; SOURCES.md | OpenAI Codex assistance is disclosed. Candidate must confirm no other tools/services were used.
Key rule | Commercial-use dependency licensing | Partial | SOURCES.md; pyproject.toml | Resolved Windows dependency licenses inventoried; dependencies are not locked and Linux/container SBOM is not complete.
Key rule | Media/data rights and no real-world outreach | Yes (current repository) | SOURCES.md; README.md; config/; examples/ | No media/datasets found; synthetic examples. Use local instances or partner-agreed sandbox only.
Reviewer access | All files/links accessible to admin@incubrix.com | No | Git has no remote/commits; no live URL | Create private repo or upload package and grant reviewer access before submission.